## Slide 1
DSA Season
Dirt Gravel and Low Volume Road Program
WEBINAR
If you are reading this, then you are successfully seeing the webinar video. Webinar audio should be automatic through your computer (or click “join audio”), and options can be accessed in the “audio options” button on the bottom left. If your computer audio is not working, you can listen on your phone by dialing 646-876-9923.
3/21/24 Starts at 9am
Audio via Phone if needed: 646-876-9923
Webinar ID: 987 5482 6192
Dave Morrison- CDGRS
Steve Bloser - CDGRS
www.dirtandgravelroads.org

## Slide 2
  Driving Surface Aggregate
    Placement Season April through September
    110,000 tons placed in 2023 (SCC funds only)
    @ $40 a ton, that’s $4.4 Million or roughly 25% of overall DGR roject spending

## Slide 3
DSA Season Prep
  Purpose
  Primer and reminder for DSA placement season starting April 1
  Discussion of new DSA Project Checklist

## Slide 4
RESOURCES:
DSA Certification: 2 page DSA certification form
DSA Specification: Material & Placement specs
DSA Handbook: More in depth DSA explanation
- Includes Request for Quote
- more details to come
All can be found on the CDGRS website including this webinar.
DSA Season Prep
Notes: In your course book are the resources noted here (on screen). There is also an Aggregate Handbook available which thoroughly covers DSA.

## Slide 5
DSA RESOURCES:
DSA Handbook: More in depth DSA information
  includes Request for Quote
  www.dirtandgravelroads.org
  Municipal DSA Quick Guide:
Questions?
DSA Season Prep
Resources
Notes: In your course book are the resources noted here (on screen). There is also an Aggregate Handbook available which thoroughly covers DSA.

## Slide 6
Reminder: 2023 DSA Changes:
Material
Slight gradation change. #200 11%-15% (17% if PI <2)
Placement
Placement Season April 1 through September 30 unless approved by SCC – NO GUARANTEE!
Paver must place DSA in single pass (paver still not required for jobs less than 500 tons)
DSA Season Preparation

## Slide 7
DSA Use and Overuse
DSA Season Preparation
DSA Use
When DSA is used as part of a project, it should be the very last phase of the project.
DSA alone does not constitute a comprehensive DGLVR Program project.

## Slide 8
DSA Season Preparation
Sampling & Testing
Purchasing DSA with DGLVR Funds:
DSA must be independently sampled and tested
30-day notice time required for testing if CDGRS is doing the sampling.
Help from Center is also available for testing or placement on request.

## Slide 9
DSA Season Preparation
Sampling & Testing
Purchasing DSA with DGLVR Funds:
DSA must be independently sampled and tested
30-day notice time required for testing if CDGRS is doing the sampling.
Help from Center is also available for testing or placement on request.
30 day notice is a minimum
Notify as soon as supplier is known
Supplier needs time to make entire pile
Time for sampling
Time for testing
Potential time for failures

## Slide 10
DSA Season Preparation
Sampling & Testing
How to sample a DSA pile
Sampling and testing must be done on the (entire) specific pile that is supplying your project

## Slide 11
DSA Season Preparation
Sampling & Testing
How to sample a DSA pile
Sampling and testing must be done on the (entire) specific pile that is supplying your project
Sample the full pile required for your project, if your project requires 5,000 tons, it must be a 5,000-ton pile.
Quarries must produce DSA piles in advance of delivery in order to allow time for sampling and testing
Labs can get backlogged in construction season

## Slide 12
Can a conservation district pull their own sample?
DSA Season Preparation
Sampling & Testing
Yes. If a CD pulls their own sample, they must also pay for the lab testing.
The costs of testing can be incorporated into the project cost or paid out of admin/education funds
Sampling and testing can also be done, free of charge, by the Center’s DSA Clearinghouse (more details on that later)

## Slide 13
How to collect a DSA sample…
DSA Season Preparation
Sampling & Testing
Contact the Center and we will train at the quarry on how to properly pull a sample.
Not as simple as just putting material in a bucket!!!

## Slide 14
How much do I need for a sample?
DSA Season Preparation
Sampling & Testing
Proctor, gradation, plasticity
(2) ¾ full 5-gallon buckets (Minimum)
More buckets necessary depending on pile size and required tests
Too much sample is always better than not enough

## Slide 15
How much do I need for a sample?
DSA Season Preparation
Sampling & Testing
One additional bucket each for Soundness
And LA Abrasion if needed
pH testing is rare and can be run with minimal material

## Slide 16
DSA Season Preparation
Sampling & Testing
Lab Testing
Interested in sampling your own DSA?
Let us know. We can share logistics of sample delivery or shipping, testing, etc.

## Slide 17
DSA Season Preparation
Sampling & Testing
Lab Testing
Material must be tested by an independent lab (with no affiliation with the quarry or placement contractor) before delivery
The testing lab must be currently certified by AASHTO or PennDOT
Per the SCC specification, DSA shall not be placed without pre-delivery sampling and testing. This testing is key to catching any potential problems with the aggregate BEFORE it is placed.

## Slide 18
DSA Season Preparation
Sampling & Testing
Plasticity
Lab Testing
Example of lab results
The lab looks at more sieves than just those in the specification
This gives us a very clear snapshot of what is in the pile

## Slide 19
DSA Season Preparation
Sampling & Testing
Lab Testing
Lot-dependent tests: run on every pile
Gradation (size distribution)
Plasticity (clay content)
Periodic test: Proctor (gives optimum moisture and max dry density)
Source-dependent tests: rarely needed
Toughness (LA Abrasion)
pH
Soundness (resistance to freeze/thaw)

## Slide 20
What happens if a sample fails?
DSA Season Preparation
Sampling & Testing
Gradation
If it’s close to meeting the spec., re-sample and re-test. This is a common practice.
If it fails a second time, a new pile will have to be made
Passing Sieve | Lower % | Higher %
1½ inch | 100 | -
3/4 inch | 65 | 97
#4 (1/4 ") | 30 | 65
#16 (1/16 ") | 15 | 30
#200(1/200 ") | 11 | 15*
The DSA spec:
50.2
39.8
13.3
Spec: 15-30
Gradation run on every pile

## Slide 21
What happens if a sample fails?
DSA Season Preparation
Sampling & Testing
Plasticity
If plasticity fails, a new pile needs to be made after discussion of production methods
Some quarries may never meet this part of the spec.
Maximum allowable PI is 4 (or 2 if fines are 15-17%)
Plasticity run on every pile

## Slide 22
What happens if a sample fails?
DSA Season Preparation
Sampling & Testing
LA Abrasion
Find a new supplier. This property is a quality of the rock formation.
Its possible a new seam of rock at the quarry may perform better. Let quarry test it first.
Maximum allowable abrasion loss is 45%
Toughness rarely run

## Slide 23
What happens if a sample fails?
DSA Season Preparation
Sampling & Testing
Soundness:
Find a new supplier. This property is a quality of the rock formation.
Its possible a new seam of rock at the quarry may perform better. Let quarry test it first.
Maximum allowable soundness loss is 20%
Soundness rarely run

## Slide 24
What happens if a sample fails?
pH- Find a new supplier (one and done in most cases).
DSA Season Preparation
Sampling & Testing
DSA SPEC: pH between 6 and 12.45
pH rarely run

## Slide 25
DSA Season Preparation
DSA Clearinghouse
PURPOSE
Provide a central point of contact between conservation districts and DSA suppliers.
Provide DSA testing services when needed.
Provide DSA education to conservation districts.
Provide a central repository of DSA testing and placement data for the state to serve as a reference and avoid duplication of testing.
DSA Clearinghouse

## Slide 26
DSA Season Preparation
DSA Clearinghouse
DISTRICT RESPONSIBILITY
Contact the Center for Dirt and Gravel Road Studies when a potential DSA supplier is chosen, at least 30 days before desired placement date.
Notification can be made utilizing the DSA Purchase Notification Form, provided in Appendix D in the DSA Handbook, or on the Center’s website.
If districts choose to sample their own DSA, they should share testing results with the Center in order to provide a more comprehensive statewide database and avoid duplicate testing.
DSA Clearinghouse

## Slide 27
DSA Season Preparation
DSA Clearinghouse
DISTRICT RESPONSIBILITY
Contact the Center for Dirt and Gravel Road Studies when a potential DSA supplier is chosen, at least 30 days before desired placement date.
Notification can be made utilizing the DSA Purchase Notification Form, provided in Appendix D in the DSA Handbook, or on the Center’s website.
If districts choose to sample their own DSA, they should share testing results with the Center in order to provide a more comprehensive statewide database and avoid duplicate testing.
DSA Clearinghouse
30 day notice is a minimum
Notify as soon as supplier is known
Supplier needs time to make entire pile
Time for sampling
Time for testing
Potential time for failures

## Slide 28
DSA Season Preparation
DSA Clearinghouse
DSA Notification: CD portion
dcm35@psu.edu
Notes: New email coming…DO NOT Fax until further notice
Email Dave Morrison dcm35@psu.edu

## Slide 29
DSA Season Preparation
DSA Clearinghouse
DSA Notification: CDGRS portion
Notes: You should share these results with the quarry or tell us to share them. As far as we are concerned these lab tests are property of the CD/SCC and are privileged info

## Slide 30
DSA Clearinghouse
POTENTIAL SERVICES PROVIDED
Visiting and talking with quarries and CD to ensure they understand the DSA requirements.
Collecting samples from the quarry and performing testing to ensure DSA meets all material requirements before delivery and placement.
Providing contractor education on DSA.
Providing on-site assistance during DSA placement.
Education of Conservation District staff on DSA sampling, testing, and placement.
Troubleshooting.
Identifying potential DSA suppliers if you are having trouble finding DSA in your area
DSA Season Preparation
DSA Clearinghouse
Get on the schedule as far out as possible.

## Slide 31
NEW DSA Project Checklist/Walkthrough for CDs
3-pages
Sent in webinar reminder
Posted online

## Slide 32
DSA Season Preparation
  DSA Season Prep
  What is the DSA Project Checklist?
  Pre-application
  Pre-Project logistics
  ~30 days prior to placement
  Final Preparations
  DSA Placement

## Slide 33
DSA Season Preparation
DSA Project Checklist
What is the DSA Project Checklist?
A guide for CD’s to plan and implement successful DSA placements as part of a DGLVR project
Informational only: no NEW required actions.
Any existing required actions are noted as such

## Slide 34
DSA Season Preparation
  DSA Season Prep
  What is the DSA Project Checklist?
  Pre-application
  Pre-Project logistics
  ~30 days prior to placement
  Final Preparations
  DSA Placement

## Slide 35
DSA Season Preparation
DSA Project Checklist – Pre-application
Drainage and base first!!
DSA is not required on every project
Program focus is on long-term road and environmental improvements
Projects are required to address any drainage, road base, and environmental issues prior to DSA placement

## Slide 36
DSA Season Preparation
DSA Project Checklist – Pre-application
Meet with the municipality
Suggested An on-site pre-application meeting with the municipality helps to ensure a quality application
Discussing Topics:
  Timing: Application, drainage work, placement date(s), placement season, time for production and testing, etc
  Details: Project length, DSA depth, width, tonnage, available budget, paver, etc
  Potential suppliers & placement contractors
  Road preparation: Drainage, surface prep (fill/grading), etc
  Compaction: Will compaction testing be utilized?

## Slide 37
DSA Season Preparation
DSA Project Checklist – Pre-application
The formula below is a general guide to the amount of DSA needed based on width, depth, and length of placement.
How much DSA should I order?
DSA Road Road
Needed = Width x Length x
(tons) (ft) (ft)
0.04 for 8” loose
compacted to 6”
0.03 for 6” loose
compacted to 4½”
Material Calculation
Notes: DSA is the icing on the cake.

## Slide 38
DSA Season Preparation
  DSA Season Prep
  What is the DSA Project Checklist?
  Pre-application
  Pre-Project logistics
  ~30 days prior to placement
  Final Preparations
  DSA Placement

## Slide 39
DSA Season Preparation
DSA Checklist – Pre-project logistics
Municipalities should follow their standard purchasing, bidding, and payment procedures.
Prevailing wage applies to contracted labor when the total value of the project exceeds $25,000
An editable DSA Request for Quote is available on the Center’s website if needed
Bidding

## Slide 40
DSA Season Preparation
RFQ
RFQ: use is optional: editable version on CDGRS website

## Slide 41
DSA Season Preparation
DSA Checklist – Pre-project logistics
Once placement contractor and supplier are determined…
  Schedule target placement date, and a potential back-up date in case of delays. Allow as much time as possible for quarry to make material, sampling and testing. (Sampling delays, lab back-ups/failures)
  DSA Sampling: Quarries do not have blanket approval to supply DSA. The full pile of DSA to be used on the job is required to be sampled and tested by a third-party lab prior to placement
  The pile is approved once passing lab results are obtained

## Slide 42
DSA Season Preparation
  DSA Season Prep
  What is the DSA Project Checklist?
  Pre-application
  Pre-Project logistics
  ~30 days prior to placement
  Final Preparations
  DSA Placement

## Slide 43
DSA Placement
Dirt Gravel and Low Volume Road Program
4/10/24
Dave Morrison- CDGRS
www.dirtandgravelroads.org

## Slide 44
DSA Season Preparation
DSA Checklist – 30 Days Out
Pre-Construction Meeting
Highly Recommended An on-site pre-construction meeting with the placement contractor and the municipality helps to ensure a quality project by getting everyone on the same page

## Slide 45
DSA Season Preparation
DSA Checklist – 30 Days Out
Pre-Construction Meeting Discussion Points
Trucking Logistics:
Truck routes
Number of trucks
Staging areas (material & equipment)
Turnaround for trucks to reduce backup length.

## Slide 46
DSA Season Preparation
DSA Checklist – 30 Days Out
Pre-Construction Meeting Discussion Points
Final Road Preparation
Grading and establishing crown cross-slope (week of placement)
Establishment of paving notches and keys (just prior to placement)

## Slide 47
DSA Season Preparation
DSA Checklist – 30 Days Out
Pre-Construction Meeting Discussion Points
Equipment
Ensure paver and roller to be used meet Program and contract requirements
Paving must be done in one pass (full road width) and compacted with a minimum 10-ton vibratory roller

## Slide 48
DSA Season Preparation
DSA Checklist – 30 Days Out
Pre-Construction Meeting Discussion Points
Material Slips
Define who will be collecting material slips from delivery trucks
Material slips should be retained in project file

## Slide 49
DSA Season Preparation
DSA Checklist – 30 Days Out
Pre-Construction Meeting Discussion Points
Road Logistics
Potential road closures
Need for road construction/safety signs?
Need for flaggers?

## Slide 50
DSA Season Preparation
DSA Checklist – 30 Days Out
Pre-Construction Meeting Discussion Points
Compaction Testing (optional)
Discuss use of third party or contractor compaction testing if desired
Measures actual moisture content of material
helps for sending wet/dry trucks back
Also measures percent compaction

## Slide 51
DSA Season Preparation
DSA Checklist – 30 Days Out
Quarry/Supplier Meeting
Highly Recommended Consider meeting with quarry or supplier during production and just before placement
Make sure production is on schedule and amount is adequate for sampling/completion of project
Ensure quarry understanding of..
      SCC DSA specification
      Importance of adequate mixing
      Importance of proper moisture
      Consider talking to loader operator as well as QC technician

## Slide 52
DSA Season Preparation
DSA Checklist – 30 Days Out
Quarry/Supplier Meeting
Highly Recommended Consider meeting with quarry or supplier during production and just before placement
Make sure production is on schedule and amount is adequate for sampling/completion of project
Ensure quarry understanding of..
      SCC DSA specification
      Importance of adequate mixing
      Importance of proper moisture
      Consider talking to loader operator as well as QC technician
Make sure quarry is doing moisture testing to monitor pile
Reminder about material cert. on first load delivered

## Slide 53
DSA Season Preparation
  DSA Season Prep
  What is the DSA Project Checklist?
  Pre-application
  Pre-Project logistics
  ~30 days prior to placement
  Final Preparations
  DSA Placement

## Slide 54
DSA Season Preparation
DSA Checklist – Final Preparations
Week of Placement
Review final logistics with municipality, contractor, supplier, trucking provider to make sure all are on the same page
      Road prep (crown, base, drainage)
      Truck routes (power lines)
      Staging areas
      Availability of equipment and personnel

## Slide 55
DSA Season Preparation
DSA Checklist – Final Preparations
Weather and Cancellations:
The DSA specification states: “If freezing temperatures or precipitation are forecast that may cause the material to freeze, or prevent the material from drying out, placement shall be postponed at the discretion of the road owner, Conservation District, or aggregate supplier.”.
It will often be up to the Conservation District to make calls to postpone due to weather.
Week of Placement: Check the Weather

## Slide 56
DSA Season Preparation
DSA Checklist – Final Preparations
Day before and Day of Placement
Contact municipality, contractor, & quarry to verify placement plan
  Include engineering tech performing compaction testing (if done). Their experience level can vary.
  One last check in can eliminate problems
  Use discussion points from above to tie up any loose ends
Check road for crown, keys, notches, etc.
  Irregularities in the road base will reflect to the surface

## Slide 57
DSA Season Preparation
  DSA Season Prep
  What is the DSA Project Checklist?
  Pre-application
  Pre-Project logistics
  ~30 days prior to placement
  Final Preparations
  DSA Placement

## Slide 58
DSA Season Preparation
DSA Checklist – Placement
Day of Placement
Are transport trucks tarped as required?
Did the first load come with a certification?
    Required
    Who is collecting load slips?

## Slide 59
DSA Season Preparation
DSA Checklist – Placement
During placement
Continuously monitor…
Placement depth, width, & crown/cross-slope
  It may take several hundred feet to get the paver “dialed in”
  Yield?

## Slide 60
DSA Season Preparation
DSA Checklist – Placement
During placement
Continuously monitor…
Moisture, adequate mixing of material
  Be alert for changes in consistency
  Variations can happen throughout the day

## Slide 61
DSA Season Preparation
DSA Checklist – Placement
During placement
Continuously monitor…
Trucking logistics
  # of trucks
  Power lines
  Turnarounds, routes, flaggers, etc.

## Slide 62
DSA Season Preparation
DSA Checklist – Placement
Water pouring from truck beds…
In its wettest state, DSA should look like very low-slump concrete, better if it’s a bit drier than that
Too wet

## Slide 63
DSA Season Preparation
DSA Checklist – Placement
Too dry
Will not compact
Will come apart quickly

## Slide 64
DSA Season Preparation
DSA Checklist – Placement
During placement
Making adjustments…
Contact quarry to make adjustments.
  Use dump truck radios in remote areas
  Note time of change request and compare to load time on tickets
Send trucks back if necessary!
  Once its down on the road surface, its more difficult to fix
Visit quarry if necessary
  Unforeseen problems like personnel/equipment/moisture issues

## Slide 65
DSA Season Preparation
DSA Checklist – Placement
During placement
Compaction testing…
Utilizing a nuclear density gauge
Not required by Program
Quantitative way to quickly determine
    Density (% compaction)
    Moisture content – to compare to target moisture
Having this data can make it easier to send unacceptable loads back to the source
https://www.measur.ca/product/4640-b-surface-thin-layer-density-gauge/

## Slide 66
See DSA Handbook or Full DSA Webinar for details
COMPACTION

## Slide 67
Thank You! Questions?
Reminder: NEW DSA Project Checklist for CDs
3-pages
Sent in webinar reminder
Posted online
30 day notice is a minimum
Notify as soon as supplier is known
Supplier needs time to make entire pile
Time for sampling
Time for testing
Potential time for failures
Notes: Add contact info

## Slide 68
ESM Trainings: 12 scheduled statewide with the first one this week in Johnstown.
Stream Crossing Trainings: Conservation Districts
  May 21-23
  June 11-13
  Aug 13-15
Stream Crossing Trainings: Design Engineers
  July 1-2 Centre
  Aug 28-29 McKean
  Sep 18-19 Monroe
Administrative and Financial Trainings
  Mar 13 (Admin), Mar 14 (financial), Berks
  May 21 (Admin), May 22 (financial), Westmoreland
  July 23 (Admin), July 24 (financial), Centre
  Oct 16 (Admin), Oct 17 (financial), Luzerne
  Dec 3 (Admin), Dec 4 (financial), Venango
Other Training Notes:
Workshop: Mark your calendars for October 8-10 in Dubois.
ESM Boot Camps: Working on finalizing dates for “new hire boot camps” not held since before COVID. Currently planning for two session in September, details to come.
DEP Stream Trainings: Building off the two completed last year, the Center is holding three 1.5 day stream crossing trainings for DEP permit review staff this spring.
Course Tracker: Don’t forget the new course attendance tracker allows you to look up your, or anyone else’s, current certifications and expiration dates. https://dirtandgravel.psu.edu/education-training/course-attendance-tracker/

## Slide 69
DGLVR Program
Spending Update
  5-Year Spending Update
    All funding from agreement must be spent out by 6/30/2024
    Current CD Status as of 3/20/2024
      Spent everything: 27 DGR, 23 LVR
      Committed everything: 25 DGR, 31 LVR
      Not committed: 12 DGR, 12 LVR

## Slide 70
DGLVR Program
Spending Update
  5-Year Spending Update - Financials
    Dirt and Gravel
      Committed: $3,859,654.33
      Not Committed: $379,227.69
    Low Volume
      Committed: $2,694,288.49
      Not Committed: $564,217.31
    Total that still needs to be spent
      DGR: $4,238,882.02
      LVR: $3,258,505.80
      Total: $7,497,387.82

## Slide 71
DGLVR Program
Spending Update
  5-Year Spending Update
    If you are Green in both DGR and LVR, great job!
    If you are Red in DGR and/or LVR, you have already been contacted for a status update.
    If you are Yellow in DGR and/or LVR, expect follow-up status calls/emails.

## Slide 72
  Question:
  How do I know if I’m red, yellow, or green?
    Answer:
  If your “balance remaining” is $0 in your GIS quarterly report, you are green
DGLVR Program
Spending Update

## Slide 73
  Question:
  How do I know if I’m red, yellow, or green?
    Answer:
  If you have a “balance remaining,” and it is less than the committed remaining, you are yellow
DGLVR Program
Spending Update

## Slide 74
  Question:
  How do I know if I’m red, yellow, or green?
    Answer:
  If you have a “balance remaining” and it is greater than the committed remaining, you are red
DGLVR Program
Spending Update

## Slide 75
DGLVR Program
Spending Update
  5-Year Spending Status – DGR
  As of 3/20/2024

## Slide 76
DGLVR Program
Spending Update
  5-Year Spending Status – LVR
  As of 3/20/2024

## Slide 77
  Question:
  How do I make sure my spending is counted towards the spending requirement?
    Answer:
  Enter admin, edu, and project expenses in the GIS by 6/24/2024 (and don’t forget to click save!)
DGLVR Program
Spending Update

## Slide 78
  Question:
  What if my expenses won’t be ready to enter in GIS by 6/24/2024?
    Answer:
  Contact Ken or the SCC to discuss a plan
DGLVR Program
Spending Update

## Slide 79
  Question:
  What if I don’t know how much money I need to spend or how to spend it?
    Answer:
  Review GIS
  Review past webinars
  Reach out to Ken or the SCC for assistance
DGLVR Program
Spending Update

## Slide 80
  Question:
  What if I know I’m not going to meet my spending requirements?
    Answer:
  Reach out to Ken or the SCC to let us know.
DGLVR Program
Spending Update