## Slide 1
CDGRS
Maria Dreese
maa241@psu.edu
Clarion Conservation District
Alicia Ramsey
ramseyccd@gmail.com
Warren County Conservation District
Heather Wilcox
hwilcox@wcconservation.net
SPREAD FOOTER BRIDGES
Dirt Gravel and Low Volume Road Program
January 19, 2023

## Slide 2
Spread Footer vs. Traditional Abutments
  When to Consider a Spread Footer
  Pros & Cons
Spread Footer Project Installation Sequence - Barr Road, Indiana County
Clarion County Gowdy Road Project
Warren County Stoddard Road Project
SPREAD FOOTER BRIDGES

## Slide 3
Traditional Bridge Abutments
www.dirtandgravelroads.org
McCormick Taylor

## Slide 4
Traditional Bridge Abutments
www.dirtandgravelroads.org
Low Flow Channel
Wisconsin DOT

## Slide 5
Traditional Bridge Abutments
www.dirtandgravelroads.org
Beaver County

## Slide 6
Traditional Bridge Abutments
www.dirtandgravelroads.org
Beaver County

## Slide 7
Traditional Bridge Abutments
www.dirtandgravelroads.org
Wayne County

## Slide 8
Spread Footer Foundations
www.dirtandgravelroads.org
Traditional Footer
Spread Footer

## Slide 9
Spread Footer Foundations
www.dirtandgravelroads.org

## Slide 10
Spread Footer Foundations
www.dirtandgravelroads.org
Existing Road Surface Elevation
Existing Road Base

## Slide 11
Spread Footer Foundations
www.dirtandgravelroads.org
Spread Footer Foundation
Traditional Bridge Abutment

## Slide 12
When to Consider A Spread Footer
www.dirtandgravelroads.org
Bankfull measurements that require structures 20’ span or greater
*~16.25 Bankfull Width
Areas that require additional opening area to meet the Q100 at 80% of the structure capacity
Areas where the vertical rise is limited for roadway elevation but additional span (width) is necessary
Stream channels that exceed 4% continuity slope and require a bottomless structure

## Slide 13
Pros & Cons
www.dirtandgravelroads.org
Pros
Reduced depth of excavation
Less concrete and sequential concrete pours = less concrete cure time
Expedited installation schedule = less environmental and community impact
Increase structure capacity, better flood resiliency, lower maintenance requirements
Cons
Longer bridge spans required
Cost analysis to determine if reduction in abutment costs offsets additional structure length expense
Alternative design approach from Penn DOT Standard – may require additional discussion and coordination with design engineer and bridge inspectors.

## Slide 14
Spread Footer vs. Traditional Abutments
  When to Consider a Spread Footer
  Pros & Cons
Spread Footer Project Installation Sequence - Barr Road, Indiana County
Clarion County Gowdy Road Project
Warren County Stoddard Road Project
SPREAD FOOTER BRIDGES

## Slide 15: Indiana County
Green Township Barr Road
Spring 2020

## Slide 16: Existing Inlet 5’ Round Plastic Pipe

## Slide 17: Existing Inlet 5’ Round Plastic Pipe

## Slide 18: Existing Inlet

## Slide 19: Upstream Conditions

## Slide 20: Existing Structure Downstream Outlet

## Slide 21: Existing Structure Outlet Downstream Conditions

## Slide 22: Existing Conditions Roadway Approach

## Slide 23: Existing Conditions Roadway Approach

## Slide 24: Proposed Plan

## Slide 25: Proposed Plan

## Slide 26: Proposed Plan

## Slide 27: River Left Spread Footer Foundation Excavation

## Slide 28: River Left Spread Footer Foundation Excavation & Drainage

## Slide 29: River Left Spread Footer Foundation Excavation & Drainage

## Slide 30: River Left Spread Footer Foundation Base Compaction

## Slide 31: River Left Spread Footer Foundation Based Prepared

## Slide 32: River Left Spread Footer Rebar Reinforcement

## Slide 33: River Left Spread Footer Form and Rebar Reinforcement

## Slide 34: River Left Spread Footer

## Slide 35: Temporary Stream Bypass Stream Channel Restoration

## Slide 36: Stream Channel Restoration and Streambank Stabilization

## Slide 37: River Right Spread Footer Framing

## Slide 38: Completed Stream Channel Restoration & Streambank Stabilization

## Slide 39: Delivery of Pre-Fabricated Modular Bridge ~9:00 am

## Slide 40: Placement of Bridge on Spread Footers

## Slide 41: Installation of Wood Deck

## Slide 42: Installation of Wood Deck Panels

## Slide 43: Securing of Wood Deck Panels to Superstructure

## Slide 44: Expansion Anchor of Bridge to Spread Footers

## Slide 45: Fixed Attachment of Bridge Superstructure to Spread Footer

## Slide 46: Bridge Superstructure

## Slide 47: Bridge Deck & Guide Rail Installation ~7:00 pm

## Slide 48: Grading and Site Restoration Work

## Slide 49: Stream Restoration Low Water Level

## Slide 50: Downstream Condition Post Construction

## Slide 51: Upstream Condition Post Construction

## Slide 52: Final Project

## Slide 53: May 5, 2022 ~ 2 years post construction

## Slide 54: Scope of Work Included: Removal of Existing Structure Installation (2) Spread Footer Abutments Stream Channel and Bank Restoration 50’ x 20’ Pre-Fab Modular Bridge & Installation (4) New Cross Pipes Roadway Bridge Approach Work Completed in 4 Weeks Due to Weather and COVID 19 Delays Total Project Value $186,402.22

## Slide 55
Spread Footer vs. Traditional Abutments
  When to Consider a Spread Footer
  Pros & Cons
Spread Footer Project Installation Sequence - Barr Road, Indiana County
Clarion County Gowdy Road Project
Warren County Stoddard Road Project
SPREAD FOOTER BRIDGES

## Slide 56
Clarion County Gowdy Road - BEFORE
www.dirtandgravelroads.org
Gowdy Road, Washington Township, Clarion County
McCauley Run, EV stream
Notes: Where, when, why it need replacement..

## Slide 57
Clarion County Gowdy Road - BEFORE
www.dirtandgravelroads.org
Notes: Where, when, why it needed replacement..

## Slide 58
PLANNING PROCESS
www.dirtandgravelroads.org
Applicant requested tech assist
‘Pre-app’ meeting: applicant, CDGRS, District, and District engineer
TU and CDGRS survey
RFP process to select engineer (including on site meeting)
‘Pre-design’ mtg.: applicant, chosen engineer, CDGRS, District
Design and GP
Pre-bid meeting (x2): applicant, CDGRS, District, potential contractors
Construction
YEAR
Notes: Process: steps 1-8 over the timespan of Nov 2019- Aug-2022 (covid in between)

## Slide 59
DURING CONSTRUCTION
www.dirtandgravelroads.org
Ex. concrete
Before- Outlet
During
Ex. concrete
Notes: Staged, laid things out, demo, install of each practice, structure, remaining items, with some hiccups in between.
Specific items that paid off to be on site practically the entire project: E&S controls, footer placement, riprap/geo placement for bank layback (under structure), etc.

## Slide 60
COMPLETED PROJECT
www.dirtandgravelroads.org
20’ x 60’ bridge,
Instream grade controls (4), modified mud sill, & root wad revetment
Overall project cost: $312,000
Notes: Standing/ Facing same direction as 1st photo. Note elevation change lends to positive drainage away from the structure

## Slide 61
COMPLETED PROJECT
www.dirtandgravelroads.org
Notes: Standing/ Facing same direction as 1st photo. Note elevation change lends to positive drainage away from the structure

## Slide 62
SUMMARY OF EXPERIENCE
www.dirtandgravelroads.org
Lessons learned
Advantages to this type of structure
Time investment
Notes: Lessons learned- and there are many- lots of coordination. More details and improvement on the planning side may make for easier construction and oversight during.

## Slide 63
Spread Footer vs. Traditional Abutments
  When to Consider a Spread Footer
  Pros & Cons
Spread Footer Project Installation Sequence - Barr Road, Indiana County
Clarion County Gowdy Road Project
Warren County Stoddard Road Project
SPREAD FOOTER BRIDGES

## Slide 64
Warren County Stoddard Road - BEFORE
www.dirtandgravelroads.org
Outlet Looking Upstream
Inlet End of Multiple Pipes

## Slide 65
PLANNING PROCESS
www.dirtandgravelroads.org
Multiple Pre-Application site visits and project planning - Feb. through Oct. 2018
Application Received Nov. 2, 2018 & approved for funding by CD Board on Dec. 18, 2018
Held Contract signing meeting March 2019
Multiple conversations and site visits with Engineer to develop site plans, GP11 permit package, and Bid Package – March 2019 through June 2020
Public Ad in local newspaper June 29 and July 6, 2020
Mandatory site showing held July 10, 2020
Bid opening July 21, 2020
Construction began August 31, 2020 and ended November 2020

## Slide 66
DURING CONSTRUCTION
www.dirtandgravelroads.org

## Slide 67
COMPLETED PROJECT
www.dirtandgravelroads.org

## Slide 68
SUMMARY OF EXPERIENCE
www.dirtandgravelroads.org
Final Project Value: $217,775
  In addition to the stream crossing this included 16 cross pipes, 2,905 tons road fill, seeding, mulching and instream restoration work.
No Road Closures Due to Flooding Since Project Completion
  Better high-water flow under the new bridge
  Series of (15) - 12 inch pipes provide flood relief through the road profile.
Township has another LVR project to replace a multiple pipe crossing on a tributary to this stream
Lessons Learned
  Compaction of material right up to structure
  Streams are going to flood - Plan for it!
  Be as detailed as possible in your plan drawings and bid package.

## Slide 69
QUESTIONS?
Special Thank You to:
Clarion Conservation District
Warren County Conservation District
Indiana County Conservation District
SPREAD FOOTER BRIDGES